ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Armenia

## Contracting authority

“Vanadzor Municipality Staff” Community Management Institution (from now on “Vanadzor Municipality”)

## Country background

Armenia local government system is 26 years old. Since 1996 it has been passing a long way towards its sustainability, viability and efficiency, particularly when Armenia became a member of the Council of Europe in 2001 and signed, among other documents, the European Charter of Local Self-Government, which entered into force on 1 May 2002. In 2002, the new Law on Local Self-Governance has been adopted taking into account many of the commitments of Armenia to Council of Europe.

On 13 May 2013, Armenia ratified the Additional Protocol to the European Charter of Local Self-Government on the right to participate in the affairs of a local authority (Utrecht, 2009, CETS No. 207). The provisions of the Additional Protocol became part of Armenian legislation (RA Law on local self-government) on 19 June 2013. On its way to continuous improvement, Armenia has already has committed to all articles of the European Charter of local Self-Government.

On 26 March 2014, the Congress of Local and Regional Authorities of Council of Europe adopted Recommendation 351 (2014) on local democracy in Armenia. The Congress acknowledged the efforts made by the Armenian authorities to implement the provisions of the European Charter of Local Self-Government, while at the same time identified a number of areas of concern, such as the existence of numerous small municipalities, the limited powers and own resources of local authorities, the weak capacity of community councils and calling for further improvement.

Decentralisation and the creation of a strong local government system remains a priority for Armenian authorities. On 23 November 2015, following positive results of referenda on consolidation in three pilot clusters (Dilijan, Tumanyan and Tatev), the Parliament passed a package of legislative amendments to a number of laws, establishing the legal framework for the implementation of consolidation in the pilot clusters.

The constitutional referendum of 6 December 2015, introducing a shift to parliamentary governance on the national level, paved the way for further legal reforms in the field of local self-government. These reforms aim at strengthening the role of local councillors, particularly by enhancing their supervisory powers, giving emphasis to the role of inter-community bodies and organisations for enhancing the efficiency of local self-government. Constitutional provisions provide for the possibility of indirect elections of the community leaders and partisan structure of the community councils.

## Current situation in the sector

Currently, municipalities in Armenia need to constantly improve their capacities, knowledge and skills to mobilize more resources to ensure efficient and quality service delivery. In the course of public administration reforms the opportunities and potential of amalgamated communities are being increased, along with challenges they encounter as newly reformed communities.

The amalgamated communities are gradually becoming competitors to the large cities. Vanadzor is the third largest city of Armenia. Like other local governments, despite visible progress over years, it has been experiencing many challenges on the way of improvement of good governance, public participation, and municipal services. However, the potential competition from amalgamated communities provokes Vanadzor to further improve the efficiency and quality of municipal services. In addition, given the public demand of continuous improvement of municipal services and good governance, Vanadzor Municipality is keenly interested in further strengthening the capacities of its service provision departments, knowledge and skills of the municipal employees, get familiar with local and international best practices, leverage funding from alternative sources, and ensure broader transparency and visibility of municipal activities.

## Related programmes and other donor activities

Currently, Vanadzor Municipality has been cooperating with different international organizations – EUD, EU Black Sea CBC, GIZ, World Vision, etc. Through different project, these organizations supports the municipality to improve its administrative and financial management, make investments in municipal infrastructure.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

The overall objective of the ABC.GoV is to contribute to the sustainable urban governance of the cities of Vanadzor and Gyumri, Armenia:

1․2 The project anticipates to achieve the following outcomes:

### The municipalities of Vanadzor and Gyumri design and implement urban planning, waste recycling and transportation policies in line with national and European standards.

### Users of municipal transports and waste management services have access to safe, healthy, inclusive and green services.

### The residents of Vanadzor and Gyumri are more knowledgeable and aware of adverse effects of plastic waste and fuel transportation on human health and environment, change behaviour to contribute improvement of service delivery.

### Vanadzor, Gyumri, and Piła municipal employees are more knowledgeable and skilled in urban governance and service delivery.

### The project has rigorous management, monitoring, accountability, reporting and visibility mechanisms to ensure proper implementation and high visibility of the progress.

## Specific objective(s)

The specific objectives (Outcomes) of this contract are as follows:

Under current assignment, the selected international urban planning (development) expert will work closely with local an urban planning as well as with policy and legal experts in urban planning issues to support the project team in designing and facilitation of the taskforce meetings related to urban planning issues in Vanadzor and Gyumri. As soon as the issues in urban planning are identified, the international urban planning expert will assist local experts in urban planning and legal and policy issues in policy and legal drafting. Draft amended documents in urban planning will be presented in town-hall meetings for the discussion and input of Vanadzor and Gyumri residents and CSOs. The finalized version of the developed policy and regulatory documents will be submitted to the approval of the task-force members.

The selected international urban planning (development) expert will provide consultancy and technical assistance to local experts and the project team in developing ToRs and other documents in urban planning, provide urban planning expertise to GIS and Geodesy survey and mapping experts.

The international expert also is expected to provide a brief analytical report on best practices in EU countries related to urban planning and GIS policies, procedures and practices.

- The project description of action is attached and highly encouraged to go through it to ensure more comprehensive understanding of the project context and the proposed assignment within this context.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

Draft policy and legal documents on urban planning issues in Vanadzor and Gyumri approved by the project team.

Due to the cooperative work between urban planning (development) expert with GIS and Geodesy survey and mapping experts in the target cities will be able to use the spatial query and mapping functions of GIS to analyze the existing situation in the city.

- A brief analytical report on best practices in EU countries related to urban planning and GIS policies, procedures and practices is in place.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

ABC.GoV will initiate the creation of a policy and regulatory improvement Task-force (TF) comprising 20-25 members. In the course of 1.5 project years, the TF will serve as a forum for prioritizing and deliberating improvements in policy and regulatory framework at local level, its synchronizing with national and international requirements to ensure more efficient and sustainable urban governance. It will consist of the representatives of Vanadzor and Gyumri local governments, Ministry of territorial administration and infrastructure, Cadaster Committee, urban development committee, local educational institutions and businesses.

In the course of 7 TF meetings with the help of the local and international expert TF members will draft policy and regulatory documents or amendments to the existing documents in the fields of waste management and recycling, urban planning and public transportation. Those draft documents will receive feedback from Vanadzor and Gyumri residents and civil society and after finalization will be submitted to the approval of the city councils of Vanadzor and Gyumri.

Both Vanadzor and Gyumri municipalities need to have GIS. After the Study tour to the EU partner city the staff of the urban planning departments of the Vanadzor and Gyumri from the EU peer why GIS is necessary, how it operates, what are the data collection, analysis and dissemination standards. Capacity building will be based on the Infrastructure for Spatial Information in the European Community (INSPIRE) Directive requirements (https://www.youtube.com/watch?v=xew6qI-6wNk&feature=emb_logo), which aims to create European Union (EU) spatial data infrastructure for EU environmental policies or activities that may have an impact on the environment. Compliance with EU INSPIRE is another peer learning process, during which the cities will take into account number of common principals agreed on and applied by EU member states cities. After the Study tour, the ABC.GoV will procure and install GIS for Vanadzor and Gyumri Municipalities. The trained staff will start the data collection and input process. Geographic survey and mapping also will be conducted. The relevant municipal departments and other agencies and institutions will regularly supply data for GIS. The 2 municipalities will closely work with the RA Cadaster Committee and RA Committee of Urban Development to synchronize data collection and processing system to meet national data requirements – structure-wise and content-wise.

## Risks

- Local government elections,

- Unstable political situation in the country,

- Unexpected circumstances in regards of increased cases of Covid-19.

# SCOPE OF THE WORK

## General

### Description of the assignment

The Deliverables expected for the implementation of the assignment are detailed in the table below:

Deliverable

Provide report and recommendations on the assignment

Brief analytical report on best practices in EU regarding urban planning and GIS application.

Reviewed documents

### Geographical area to be covered

Vanadzor and Gyumri, Armenia

### Target groups

The target group of the ABC.GoV are 3 municipalities (Vanadzor, Gyumri, Pila). 30 municipal employees will be capacitated through the peer learning (study tours) to have key roles in renewing urban governance policies and running upgraded green infrastructure (eco-transportation and waste recycling facility). Relevant and interested CSOs, 2,000 residents, and 4,000 school-children from 40 schools, as well as higher education institutions, vocational and educational training (VET) institutions in order to reach future teachers, managers and entrepreneurs, private business owners, larger employers and cultural institutions of target cities will directly benefit from environmental education and training. A Final Beneficiaries are 90,000 residents of Vanadzor, 120,000 residents of Gyumri, and 70,000 residents of Pila: they will benefit from better policies, improved public spaces due to local green deal initiatives, will have access to a cleaner environment due to eco-transportation, waste separation, and recycling, will be aware of adverse effects of carbon emissions on health and enviroment. 30 municipalities from Armenia and EU/EaP will benefit from participating in the networking conference on sustainable urban governance.

## Specific work

The Level of Effort for the International expert is set out below:

| N | Tasks | Expert days (up to) |
| --- | --- | --- |
|  | Provide input in drafting policy and legal documents on urban planning issues in Vanadzor and Gyumri based on the priorities identified by taskforce members, assist in finalizing policy and legal document | 5 |
|  | Provide brief analysis on best practices in EU countries regarding urban planning and GIS application | 3 |
|  | Provide assistance in developing terms of reference related to the urban planning issues within the framework of the project. | 6 |
|  | Provide consultancy and technical assistance to GIS, Geodesy survey and mapping experts (data collection, analysis, conceptual and detailed plan preparation, city planning, social, economic, environmental, spatial, and other data from community development, historic preservation, or urban design, etc.). | 5 |
|  | Provide report and recommendations on the assignment | 1 |
|  | Total | 20 |

## Project management

### Responsible body

“Vanadzor Municipality Staff” Community Management Institution, represented by ABC.GoV Project

### Management structure

Vanadzor Municipality will coordinate all aspects of the technical assistance through the Alliance for Better City Governance (ABC.GoV) Project.

# LOGISTICS AND TIMING

## Location

Vanadzor and Gyumri Cities, Armenia.

## Start date & period of implementation of tasks

The intended start date is 01 September 2022 and the period of implementation of the contract will be 21 months from this date (until 31 may 2024). Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

Concrete start date of each task and detailed task descriptions will be provided in the contract related to each task.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Expert qualifications and skills

- University degree urban planning and regional development or in a related fields.

- Hold a Degree(s) in urban planning or equivalent qualifications.

- Have at least 3 yrs. urban planning and development experience.

- Demonstrate high levels of proficiency with Microsoft Word, Excel, Adobe Graphics Suite (Illustrator, Photoshop, and InDesign), Mapinfo, QGIS, ArcGIS.

- The expert must have the skills to share or teach his / her experience.

- Present excellent team work ability to operate in a variety of field and office conditions working in cross-cultural settings.

- Demonstrate clear skills in English. as well as high-quality skills in dialogue and presentation of information (knowledge of English).

### Other experts, support staff & backstopping

CVs for general staff other than the experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original:

- Inception Report of maximum 3 pages to be produced after 3 months from the start of implementation. In the report the contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report.

- Interim reports of maximum 10 pages. The contractor shall draw up interim reports during the period of implementation of the tasks. As a reminder, Article 29 of the general conditions indicate that annual interim payments can be envisaged for global price service contracts of a duration of more than two years, on the basis of approval of interim reports proving that specific objectives have been reached.

Draft final report of maximum 50 pages. This report shall be submitted no later than one month before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 10 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on activities. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

- These reports shall consist of a narrative section and a financial section. The format of such reports is as notified to the contractor by the project manager during the period of implementation of the tasks.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Monitoring and evaluation of the activity will be provided in accordance with the Vanadzor Municipality's policies and procedures.