ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Armenia

## Contracting authority

“Vanadzor Municipality Staff” Community Management Institution (from now on “Vanadzor Municipality”)

## Country background

Armenia local government system is 25 years old. Since 1996 it has been passing a long way towards its sustainability, viability and efficiency, particularly when Armenia became a member of the Council of Europe in 2001 and signed, among other documents, the European Charter of Local Self-Government, which entered into force on 1 May 2002. In 2002, the new Law on Local Self-Governance has been adopted taking into account many of the commitments of Armenia to Council of Europe.

On 13 May 2013, Armenia ratified the Additional Protocol to the European Charter of Local Self-Government on the right to participate in the affairs of a local authority (Utrecht, 2009, CETS No. 207). The provisions of the Additional Protocol became part of Armenian legislation (RA Law on local self-government) on 19 June 2013. On its way to continuous improvement, Armenia has already has committed to all articles of the European Charter of local Self-Government.

On 26 March 2014, the Congress of Local and Regional Authorities of Council of Europe adopted Recommendation 351(2014) on local democracy in Armenia. The Congress acknowledged the efforts made by the Armenian authorities to implement the provisions of the European Charter of Local Self-Government, while at the same time identified a number of areas of concern, such as the existence of numerous small municipalities, the limited powers and own resources of local authorities, the weak capacity of community councils and calling for further improvement.

Decentralisation and the creation of a strong local government system remains a priority for Armenian authorities. On 23 November 2015, following positive results of referenda on consolidation in three pilot clusters (Dilijan, Tumanyan and Tatev), the Parliament passed a package of legislative amendments to a number of laws, establishing the legal framework for the implementation of consolidation in the pilot clusters.

The constitutional referendum of 6 December 2015, introducing a shift to parliamentary governance on the national level, paved the way for further legal reforms in the field of local self-government. These reforms aim at strengthening the role of local councillors, particularly by enhancing their supervisory powers, giving emphasis to the role of inter-community bodies and organisations for enhancing the efficiency of local self-government. Constitutional provisions provide for the possibility of indirect elections of the community leaders and partisan structure of the community councils.

## Current situation in the sector

Currently, municipalities in Armenia need to constantly improve their capacities, knowledge and skills to mobilize more resources to ensure efficient and quality service delivery. In the course of public administration reforms the opportunities and potential of amalgamated communities are being increased, along with challenges they encounter as newly reformed communities.

- The amalgamated communities are gradually becoming competitors to the large cities. Vandazor is the third largest city of Armenia. Like other local governments, despite visible progress over years, it has been experiencing many challenges on the way of improvement of good governance, public participation, and municipal services. However, the potential competition from amalgamated communities provokes Vanadzor to further improve the efficiency and quality of municipal services. In addition, given the public demand of continuous improvement of municipal services and good governance, Vanadzor Municipality is keenly interested in further strengthening the capacities of its service provision departments, knowledge and skills of the municipal employees, get familiar with local and international best practices, leverage funding from alternative sources, and ensure broader transparency and visibility of municipal activities.

## Related programmes and other donor activities

Currently, Vanadzor Municipality has been cooperating with different international organizations – EUD, EU Black Sea CBC, GIZ, World Vision, etc. Through different project, these organizations supports the municipality to improve its administrative and financial management, make investments in municipal infrastructure.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is:

The overall objective of the ABC.GoV is to contribute to the sustainable urban governance of the cities of Vanadzor and Gyumri, Armenia:

The project anticipates to achieve the following outcomes:

- The municipalities of Vanadzor and Gyumri design and implement urban planning, waste recycling and transportation policies in line with national and European standards.

- Users of municipal transports and waste management services have access to safe, healthy, inclusive and green services.

- The residents of Vanadzor and Gyumri are more knowledgeable and aware of adverse effects of plastic waste and fuel transportation on human health and environment, change behaviour to contribute improvement of service delivery.

- Vanadzor, Gyumri, and Piła municipal employees are more knowledgeable and skilled in urban governance and service delivery.

The project has rigorous management, monitoring, accountability, reporting and visibility mechanisms to ensure proper implementation and high visibility of the progress.

## Specific objective(s)

The specific objectives (Outcomes) of this contract are as follows:

- To prepare public information materials for the social/outreach activities related to community mobilization, town-hall meetings organization and public hearings; and other community outreach activities deriving from the ABC.GoV action (program) description;

- Under the guidance of the project team take a leading role in actual planning of all social/outreach activities related to community mobilization, town-hall meetings organization and public hearings and other community outreach activities foreseen under the ABC.GoV Action description; collect feedback from participants, as well as comments and suggestions.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

- Residents of target communities are aware of and intensively participate in the project through the implementation of the social/outreach activities related to community mobilization, town-hall meetings organization and public hearings; and other community outreach activities deriving from the ABC.GoV action (program) description.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The aim of the project is to promote sustainable and green management of the urban governance of Vanadzor and Gyumri through improvement of policies, procedures and services in this area.

With the financial support of the European Union, Vanadzor and Gyumri, the second and the third largest cities of Armenia, assisted by their European partner city Pila from Poland, are embarking on a process of strengthening urban governance. This will be done by creating institutional capacities to address some of the priority gaps in governance and by bringing European experience and knowledge closer to the Armenian context.

Vanadzor and Gyumri Municipalities have policies and procedures which contribute to sustainable and innovative urban planning, waste recycling and "green” public transportation.

The Municipalities operate “green” public transportation with electronic ticketing system, plastic recycling production line producing construction materials for improvement of public spaces.

Public knowledge and information on adverse effects of plastic waste and carbon emissions in public health and environment is improved.

Technical capacities of municipal staff to operate new urban planning,   	waste management and transportation facilities are enhanced.

In the framework of the of the ABC.GoV project the expert should assist the project team in developing and implementing social/outreach activities foreseen under the project.

The experts should ensure community mobilization during the project implementation period including but not limited to direct communication with project communities stakeholders – residents, CSOs, businesses, schools, academic institutions, etc.; help to organize town-hall meetings organization and public hearings.

## Risks

- Local government elections;

- Unstable political situation in the country

- Unexpected circumstances in regards of increased cases of Covid-19.

# SCOPE OF THE WORK

## General

### Description of the assignment

The Deliverables expected for the implementation of the assignment are detailed in the table below:

Deliverables

- Public information materials for the social/outreach activities related to community mobilization, town-hall meetings and public hearings

- Activity reports on the public outreach activities.

- Final report

### Geographical area to be covered

Vanadzor and Gyumri communities

### Target groups

The target group of the ABC.GoV are 3 municipalities (Vanadzor, Gyumri, Pila). 30 municipal employees will be capacitated through the peer learning (study tours) to have key roles in renewing urban governance policies and running upgraded green infrastructure (eco-transportation and waste recycling facility). Relevant and interested CSOs, 2,000 residents, and4,000 school-children from 40 schools, as well as higher education institutions, vocational and educational training (VET) institutions in order to reach future teachers, managers and entrepreneurs, private business owners, larger employers and cultural institutions of target cities will directly benefit from environmental education and training. A Final Beneficiaries are 90,000 residents of Vanadzor, 120,000 residents of Gyumri, and 70,000 residents of Pila: they will benefit from better policies, improved public spaces due to local green deal initiatives, will have access to a cleaner environment due to eco-transportation, waste separation, and recycling, will be aware of adverse effects of carbon emissions on health and environment. 30 municipalities from Armenia and EU/EaP will benefit from participating in the networking conference on sustainable urban governance.

The PSAs will deliver to residents of cities a clear message developed jointly by the partners in the knowledge management workshop in Vanadzor. PSAs will relate to prevention and reduction of greenhouse gases through eco-friendly public transportation and will encourage reducing and recycling of plastic waste. The PSAs scenarios will be tested in the focus groups before production. PSAs will be aired for several weeks, before and after the special bins for plastic waste, recycling production lines are installed and electric transportation operated.

## Specific work

4.2.1 The Level of Effort for the Consultant is set out below:

| N | Tasks | Expert days (up to) |
| --- | --- | --- |
|  | Prepare public information materials for the social/outreach activities related to community mobilization, town-hall meetings and public hearings; and other community outreach activities deriving from the ABC.GoV action (program) description; | 20 |
|  | Take a leading role in actual organization and implementation of all social/outreach activities related to community mobilization, town-hall meetings organization and public hearings and other community outreach activities foreseen under the ABC.GoV Action description; collect feedback from participants, as well as comments and suggestions. | 45 |
|  | Provide inputs for preparation of final report | 5 |
|  | Total | 70 |

4.2.2 Key Qualifications

- Bachelor’s Degree in Social Sciences, in Governance, and related fields.

- At least 3 years’ experience in community development.

- Knowledge of local government system, will be advantage.

- Demonstrate clear and concise written skills in English. as well as skills in dialogue and presentation of information.

- Any combination of education and experience which provides the tenderer with the desired skills, knowledge, and ability required to perform the job.

## Project management

### Responsible body

“Vanadzor Municipality Staff” Community Management Institution, represented by ABC.GoV Project

### Management structure

Vanadzor Municipality will coordinate all aspects of the technical assistance through the Alliance for Better City Governance (ABC.GoV) Project.

# LOGISTICS AND TIMING

## Location

Vanadzor and Gyumri Cities, Armenia.

## Start date & period of implementation of tasks

The intended start date is 30 September 2022 and the period of implementation of the contract will be 21 months from this date (until 31 May 2024). Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

Provisionally, the contract will be signed for 12 months and will be extended automatically beyond that period upon availability of funds by contracting authority.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

The relevant expert can be sent on a business trip within the scope of the Project. The expenses of the business trip of this expert are reimbursed by the contracting authority in accordance to the legislation of the Republic of Armenia.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in <English and Armenian> in one original and 1 copies:

The contractor submits a draft written descriptive report after implementation of task(s). The contractor should proceed with his/her work unless the contracting authority sends comments on the draft written descriptive report.

Final report (maximum 12 pages) with the same specifications as the draft written descriptive report, incorporating any comments received from the parties on the draft report.

The deadline for sending the final report is 10 days after receipt of comments on the draft report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Monitoring and evaluation of the activity will be provided in accordance with the Vanadzor Municipality's policies and procedures.

Recommendation 351 (2014): English version: https://wcd.coe.int/ViewDoc.jsp?id=2170873&Site=COE; Armenian version: http://www.coe.am/docs/clrae/report1.pdf