ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	3

2.	OBJECTIVES & EXPECTED OUTPUTS	3

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	5

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation of tasks	5

6.	REQUIREMENTS	6

6.1.	Staff	6

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the contractor	6

6.4.	Equipment	6

7.	REPORTS	6

7.1.	Reporting requirements	6

7.2.	Submission and approval of reports	6

8.	MONITORING AND EVALUATION	6

8.1.	Definition of indicators	6

8.2.	Special requirements	7

# BACKGROUND INFORMATION

## Partner country

Republic of Armenia

## Contracting authority

“Vanadzor Municipality Staff” Community Management Institution

## Country background

Armenia local government system is 28 years old. Since 1996 it has been passing a long way towards its sustainability, viability and efficiency, particularly when Armenia became a member of the Council of Europe in 2001 and signed, among other documents, the European Charter of Local Self-Government, which entered into force on 1 May 2002. In 2002, the new Law on Local Self-Governance has been adopted taking into account many of the commitments of Armenia to Council of Europe.

On 13 May 2013, Armenia ratified the Additional Protocol to the European Charter of Local Self-Government on the right to participate in the affairs of a local authority (Utrecht, 2009, CETS No. 207). The provisions of the Additional Protocol became part of Armenian legislation (RA Law on local self-government) on 19 June 2013. On its way to continuous improvement, Armenia has already has committed to all articles of the European Charter of local Self-Government.

On 26 March 2014, the Congress of Local and Regional Authorities of Council of Europe adopted Recommendation 351 (2014) on local democracy in Armenia. The Congress acknowledged the efforts made by the Armenian authorities to implement the provisions of the European Charter of Local Self-Government, while at the same time identified a number of areas of concern, such as the existence of numerous small municipalities, the limited powers and own resources of local authorities, the weak capacity of community councils and calling for further improvement.

Decentralisation and the creation of a strong local government system remains a priority for Armenian authorities. On 23 November 2015, following positive results of referenda on consolidation in three pilot clusters (Dilijan, Tumanyan and Tatev), the Parliament passed a package of legislative amendments to a number of laws, establishing the legal framework for the implementation of consolidation in the pilot clusters.

The constitutional referendum of 6 December 2015, introducing a shift to parliamentary governance on the national level, paved the way for further legal reforms in the field of local self-government. These reforms aim at strengthening the role of local councillors, particularly by enhancing their supervisory powers, giving emphasis to the role of inter-community bodies and organisations for enhancing the efficiency of local self-government. Constitutional provisions provide for the possibility of indirect elections of the community leaders and partisan structure of the community councils.

## Current situation in the sector

Currently, municipalities in Armenia need to constantly improve their capacities, knowledge and skills to mobilize more resources to ensure efficient and quality service delivery. In the course of public administration reforms the opportunities and potential of amalgamated communities are being increased, along with challenges they encounter as newly reformed communities.

The amalgamated communities are gradually becoming competitors to the large cities. Like other local governments, despite visible progress over years, it has been experiencing many challenges on the way of improvement of good governance, public participation, and municipal services in Vanadzor and Gyumri municipalities. However, the potential competition from amalgamated communities provokes Vanadzor and Gyumri to further improve the efficiency and quality of municipal economy.

Municipalities are exposed to severe environmental pollution issues fed by industrial, agricultural and other activities combined with poor waste and sanitation management practices. Municipalities are examined through a “dual approach” as both contributors and receivers of different pollution leakage into the natural environment (through the air–water–soil–biota nexus).

Vanadzor and Gyumri municipalities must be involved in both future pollution and circular economy research to help decision makers reduce environmental and public health threats, and to catalyse circular initiatives in local economy.

## Related programmes and other donor activities

Currently, Vanadzor Municipality has been cooperating with different international organizations – EUD, EU Black Sea CBC, GIZ, World Vision, etc. Through different project, these organizations support the municipality to improve its administrative and financial management, make investments in municipal infrastructure and sectors of economy.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is:

The overall objective of the ABC.GoV is to contribute to the sustainable urban governance of the cities of Vanadzor and Gyumri, Armenia:

2.1.1 The project anticipates to achieve the following outcomes:

### The municipalities of Vanadzor and Gyumri design and implement urban planning, waste recycling and transportation policies in line with national and European standards.

### Users of municipal transports and waste management services have access to safe, healthy, inclusive and green services.

### The residents of Vanadzor and Gyumri are more knowledgeable and aware of adverse effects of plastic waste and fuel transportation on human health and environment, change behavior to contribute improvement of service delivery.

### Vanadzor and Gyumri municipal employees are more knowledgeable and skilled in urban governance and service delivery.

- The project has rigorous management, monitoring, accountability, reporting and visibility mechanisms to ensure proper implementation and high visibility of the progress.

## Specific objective(s)

The specific objectives (Outcomes) of this contract are as follows:

Specific Objective (Outcome) 1: To enhance environmental awareness and community engagement in Vanadzor and Gyumri by organizing and successfully executing city-wide clean-up days, involving residents, youth, NGOs, and schools.

Specific Objective (Outcome) 2: To promote sustainable and eco-friendly transportation practices in partner cities through the implementation of a green transportation week, encouraging residents to adopt the "green transportation hierarchy" steps and providing diverse options for environmentally conscious travel.

Specific Objective (Outcome) 3: To instill practical environmental knowledge and skills among schoolchildren in Vanadzor and Gyumri by fostering a culture of waste reduction and sustainable practices within the school communities.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

1. Output 1: Comprehensive project plan and timeline for the Clean City and Green transportation Weeks

- A detailed project plan outlining the activities, resources for the Weeks.

- A comprehensive project timeline indicating the sequence and duration of each task.

2. Output 2: Mobilized participants for Clean City week (city-wide clean-up days)

- Active involvement and participation of residents, youth, NGOs, and schools in the city-wide clean-up days in Vanadzor and Gyumri.

- Distribution of environmental messages and posters throughout the cities to raise awareness and encourage citizen participation.

3. Output 3: Plastic waste collection and disposal

- Successful distribution of sacks for collecting plastic waste during the Clean City Week.

- Proper disposal of collected plastic waste in the designated bins for plastic waste in Vanadzor and Gyumri.

4. Output 4: Increased awareness and adoption of eco-friendly transportation options

- Raised awareness among residents about the "green transportation hierarchy" and its benefits.

- Increased usage of eco-friendly transportation options such as walking, biking and carpooling.

- Enhanced knowledge and understanding of the environmental and health benefits associated with eco-friendly transportation choices.

5. Output 5: Organised city biking tours, scooter tours, and bike master-classes

- Successful organisation of city biking tours, electric and mechanical scooter tours, and bike master-classes.

- Increased participation of residents, especially youth, in these activities to promote eco-friendly transportation and physical exercise (the participants will identify their location in green transportation hierarchy before taking any action and in a week they will cross-check where they got on the green transportation hierarchy).

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

Waste management and recycling are priority for Vanadzor and Gyumri and are reflected in community development plans and Local Environmental Action Plans within the EU Covenant of Mayors. Cities either do not have waste management plans or those need improvement to include waste separation and recycling components. Waste separation is not fully practiced. A large number of bins for household waste became obsolete or are sub-standard to be lifted by garbage trucks.

The ABC.GoV will introduce an innovative plastic recycling model: the idea is to recycle the plastic mixed with sand to produce construction materials for renovation of public spaces. The technology will be tested in Vanadzor and Gyumri for the first time. The technology has been already piloted in Kapan, Armenian (Construction materials from plastic: Kapan, Armenia). Such an experience will allow to smoothly replicate the model in Vanadzor and Gyumri taking into account success elements and lessons learned.

The partner municipalities agreed that each will establish a new municipal start-up company, with a strategy to gradually shift to the public-private partnerships (PPP) arrangement.

The plastic will be stored as a result of intensive public awareness and education campaign and installing special bins for plastic in the target cities. The primary users of the produced construction materials - curbs, tiles and roof tiles will be the ABC.GoV target communities by renovating public spaces as demonstration sites. First batches of the production will be used for renovation activities in neighbourhoods, parks, public spaces under local green deal initiatives.

## Risks

- Local government elections;

- Unstable political situation in the country;

- Unexpected circumstances in regards of increased cases of Covid-19.

# SCOPE OF THE WORK

## General

### Description of the assignment

The assignment involves organizing and implementing the Clean City and Green Transportation Weeks events in partnership with the municipalities of Vanadzor and Gyumri, along with the support of NGOs, schools, and the ABC.GoV (insert the full name of the organization). The project aims to promote environmental awareness and engage the community in taking action towards a cleaner and more sustainable city.

The event will consist of two main components:

 1. Clean City week (City-wide Clean-up Days): Starting from the Clean-up Day, residents, youth, NGOs, and schools will come together to organize city-wide clean-up days in Vanadzor and Gyumri. Participants will march through the cities with posters displaying environmental messages, urging fellow citizens to keep their city and neighborhoods clean. Emphasis will be placed on encouraging the separation of plastic waste at the source (homes). Young volunteers will distribute sacks to collect plastic waste during the Clean City Week, which will then be placed in specially designated bins for plastic waste already installed in the cities. The clean-up week will be meticulously planned and coordinated in collaboration with the partner municipalities. 

2. Green Transportation Week: On International Earth Day, a green transportation week will be announced in the partner cities, facilitated by the ABC.GoV. Throughout the week, young volunteers will encourage residents to follow the "green transportation hierarchy" steps to make the cities more climate-change-resilient. The key message will be to provide multiple options for transportation, allowing individuals to choose the most suitable mode for themselves. Various activities such as city biking tours, electric and mechanical scooter tours, mountain biking and similar other influential initiatives will also be organised. This hands-on experience will enable them to apply what they have learned during environmental classes and seminars, fostering practical environmental knowledge and skills. The assignment will encompass the planning, coordination, and execution of the Clean City Week project, ensuring active community participation, effective waste management practices, and the promotion of eco-friendly transportation alternatives.

### Geographical area to be covered

Vanadzor and Gyumri, Armenia.

### Target groups

The target group of the ABC.GoV are 3 municipalities (Vanadzor, Gyumri, Pila). 30 municipal employees will be capacitated through the peer learning (study tours) to have key roles in renewing urban governance policies and running upgraded green infrastructure (eco-transportation and waste recycling facility).

Relevant and interested CSOs, 2,000 residents, and 4,000 school-children from 40 schools, as well as higher education institutions, vocational and educational training (VET) institutions in order to reach future teachers, managers and entrepreneurs, private business owners, larger employers and cultural institutions of target cities will directly benefit from environmental education and training.

A Final Beneficiaries are 90,000 residents of Vanadzor, 120,000 residents of Gyumri, and 70,000 residents of Pila: they will benefit from better policies, improved public spaces due to local green deal initiatives, will have access to a cleaner environment due to eco-transportation, waste separation, and recycling, will be aware of adverse effects of carbon emissions on health and environment. 30 municipalities from Armenia and EU/EaP will benefit from participating in the networking conference on sustainable urban governance.

## Specific work

The following is a detailed list of tasks to be undertaken to achieve the objectives of the Clean City and Green Transportation Week events.

1. Task 1: Event Planning and Coordination

- Conduct an initial assessment of the project requirements and develop a detailed event plan.

- Establish communication channels with partner municipalities, NGOs, schools, and the ABC.GoV.

- Coordinate with relevant stakeholders to define roles and responsibilities.

- Prepare a comprehensive event timeline and schedule for all activities.

2. Task 2: Clean City Week (City-wide Clean-up Days)

- Collaborate with partner municipalities to plan the city-wide clean-up days in Vanadzor and Gyumri.

- Coordinate with NGOs, schools, and volunteers to mobilize participants and ensure their active involvement.

- Develop and distribute environmental messages or posters for the march throughout the cities.

- Facilitate the distribution of sacks for plastic waste collection and coordinate their disposal in designated bins.

- Prepare a report summarising the outcomes and impact of the clean-up days.

3. Task 3: Green Transportation Week

- Plan and announce the green transportation week in collaboration with the partner cities and the ABC.GoV.

- Recruit and train young volunteers to promote the "green transportation hierarchy" steps and encourage residents to choose eco-friendly transportation options (the participants will identify their location in green transportation hierarchy before taking any action and in a week they will cross-check where they got on the green transportation hierarchy).

- Organise city biking tours/ electric and mechanical scooter tours/mountain biking classes/.

- Prepare a report evaluating the effectiveness of the green transportation week and its impact on promoting sustainable transportation practices.

Note: The contractor is responsible for ensuring the sustainability and dissemination of project outputs. The contractor must also comply with the latest Communication and Visibility Requirements for EU-funded external actions, as laid down and published by the European Commission. The contractor should develop their own detailed organisation, methodology, and technical proposals to address the general requirements outlined in these terms of reference.

## Project management

### Responsible body

“Vanadzor Municipality Staff” Community Management Institution, represented by ABC.GoV Project

### Management structure

Vanadzor Municipality will coordinate all aspects of the technical assistance through the Alliance for Better City Governance (ABC.GoV) Project.

# LOGISTICS AND TIMING

## Location

Vanadzor and Gyumri Cities, Armenia.

## Start date & period of implementation of tasks

The intended start date is 05 March 2024 and the period of implementation of the contract will be up to 3 months from this date (until 31 May 2024). Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Other experts, support staff & backstopping

The tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that the experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in Armenian and English in one original and 1 copy:

- Report in regards to delivered tasks or activities. In case of recommendations or comments provided after revision of the report by the Project manager, the tenderer should incorporate changes based on the recommendations and comments. The deadline for sending the final report is 10 days after receipt of comments on the report. The report shall contain a sufficiently detailed description of the delivered activities, tasks. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Monitoring and evaluation of the activity will be provided in accordance with the Vanadzor Municipality's policies and procedures.