ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Armenia

## Contracting authority

“Vanadzor Municipality Staff” Community Management Institution (from now on“Vanadzor Municipality”)

## Country background

Armenia local government system is 25 years old. Since 1996 it has been passing a long way towards its sustainability, viability and efficiency, particularly when Armenia became a member of the Council of Europe in 2001 and signed, among other documents, the European Charter of Local Self-Government, which entered into force on 1 May 2002. In 2002, the new Law on Local Self-Governance has been adopted taking into account many of the commitments of Armenia to Council of Europe.

On 13 May 2013, Armenia ratified the Additional Protocol to the European Charter of Local Self-Government on the right to participate in the affairs of a local authority (Utrecht, 2009, CETS No. 207). The provisions of the Additional Protocol became part of Armenian legislation (RA Law on local self-government) on 19 June 2013. On its way to continuous improvement, Armenia has already has committed to all articles of the European Charter of local Self-Government.

On 26 March 2014, the Congress of Local and Regional Authorities of Council of Europe adopted Recommendation 351(2014) on local democracy in Armenia. The Congress acknowledged the efforts made by the Armenian authorities to implement the provisions of the European Charter of Local Self-Government, while at the same time identified a number of areas of concern, such as the existence of numerous small municipalities, the limited powers and own resources of local authorities, the weak capacity of community councils and calling for further improvement.

Decentralisation and the creation of a strong local government system remains a priority for Armenian authorities. On 23 November 2015, following positive results of referenda on consolidation in three pilot clusters (Dilijan, Tumanyan and Tatev), the Parliament passed a package of legislative amendments to a number of laws, establishing the legal framework for the implementation of consolidation in the pilot clusters.

The constitutional referendum of 6 December 2015, introducing a shift to parliamentary governance on the national level, paved the way for further legal reforms in the field of local self-government. These reforms aim at strengthening the role of local councillors, particularly by enhancing their supervisory powers, giving emphasis to the role of inter-community bodies and organisations for enhancing the efficiency of local self-government. Constitutional provisions provide for the possibility of indirect elections of the community leaders and partisan structure of the community councils.

## Current situation in the sector

Currently, municipalities in Armenia need to constantly improve their capacities, knowledge and skills to mobilize more resources to ensure efficient and quality service delivery. In the course of public administration reforms the opportunities and potential of amalgamated communities are being increased, along with challenges they encounter as newly reformed communities.

The amalgamated communities are gradually becoming competitors to the large cities. Vandazor is the third largest city of Armenia. Like other local governments, despite visible progress over years, it has been experiencing many challenges on the way of improvement of good governance, public participation, and municipal services. However, the potential competition from amalgamated communities provokes Vanadzor to further improve the efficiency and quality of municipal services. In addition, given the public demand of continuous improvement of municipal services and good governance, Vanadzor Municipality is keenly interested in further strengthening the capacities of its service provision departments, knowledge and skills of the municipal employees, get familiar with local and international best practices, leverage funding from alternative sources, and ensure broader transparency and visibility of municipal activities.

## Related programmes and other donor activities

Currently, Vanadzor municipality has been cooperating with different international organizations – EUD, EU Black Sea CBC, GIZ, World Vision, etc. Through different project, these organizations supports the municipality to improve its administrative and financial management, make investments in municipal infrastructure.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

The overall objective of the ABC.GoV is to contribute to the sustainable urban governance of the cities ofVanadzor and Gyumri, Armenia:

The project anticipates to achieve the following outcomes:

- The municipalities of Vanadzor and Gyumri design and implement urban planning, waste recycling and transportation policies in line with national and European standards.

- Users of municipal transports and waste management services have access to safe, healthy, inclusive and green services.

- The residents of Vanadzor and Gyumri are more knowledgeable and aware of adverse effects of plastic waste and fuel transportation on human health and environment, change behaviour to contribute improvement of service delivery.

- Vanadzor, Gyumri, and Piła municipal employees are more knowledgeable and skilled in urban governance and service delivery.

- The project has rigorous management, monitoring, accountability, reporting and visibility mechanisms to ensure proper implementation and high visibility of the progress.

## Purpose

Under current assignment, the selected waste management expert will work closely with policy and legal expert to provide consultancy and technical assistance to the project team in improvement of waste management and recycling policies and procedures. He/she also will provide technical assistance in developing waste management plans, calculating unit cost for solid waste collection, accumulation, transportation and disposal, ToRs for purchasing waste management-related equipment and facilities as well as in providing input in preparing public information, awareness raising and educational materials related to waste management and recycling.

## Results to be achieved by the contractor

Draft policy and legal documents on waste management and recycling issues for Vanadzor and Gyumri approved by the project team. Waste management plans for Vanadzor and Gyumri are developed. Revised ToRs on purchasing waste management equipment are in place.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

ABC.GoV will initiate the creation of a policy and regulatory improvement Task-force (TF) comprising 20-25 members. In the course of 1.5 project years, the TF will serve as a forum for prioritizing and deliberating improvements in policy and regulatory framework at local level, its synchronizing with national and international requirements to ensure more efficient and sustainable urban governance. It will consist of the representatives of Vanadzor and Gyumri local governments, Ministry of territorial administration and infrastructure, cadaster committee, urban development committee, local educational institutions and businesses.

In the course of 7 TF meetings with the help of the local and international expert TF members will draft policy and regulatory documents or amendments to the existing documents in the fields of waste management and recycling, urban planning and public transportation. Those draft documents will receive feedback from Vanadzor and Gyumri residents and civil society and after finalization will be submitted to the approval of the city councils of Vanadzor and Gyumri.

Waste management and recycling are priority for Vanadzor and Gyumri and are reflected in community development plans and Local Environmental Action Plans within the EU Covenant of Mayors. Cities either do not have waste management plans or those need improvement to include waste separation and recycling components. Waste separation is not fully practiced. A large number of bins for household waste became obsolete or are sub-standard to be lifted by garbage trucks. The ABC.GoV will help target communities to purchase bins and recycling facilities:

| Vanadzor | Gyumri |
| --- | --- |
| 1 plastic recycling production line | 1 plastic recycling production line |
| 6 types of moulds | 6 types of moulds |
| 300 bins for mixed waste | 330 bins for mixed waste |
| 300 bins for plastic waste | 330 bins for plastic waste |
| 1 sweeper truck | 1sweeper truck |
| 2 balers | 2 balers |
| 1 cleaning/disinfection machine | 1 cleaning/disinfection machine |

Once purchased at the end of the project Year 1, the equipment/facilities will be operated along with the public education campaign.

## Risks

- Local government elections;

- Unstable political situation in the country

- Unexpected circumstances in regards of increased cases of Covid-19.

# SCOPE OF THE WORK

## General

### Description of the assignment

The Deliverables expected for the implementation of the assignment are detailed in the table below:

Deliverable

Report and recommendations on the assignment

Local Waste Management plans for Vanadzor and Gyumri

Reviewed ToRs

Reviewed local policies and ordinances in waste management

### Geographical area to be covered

Vanadzor and Gyumri, Armenia

### Target groups

The target group of the ABC.GoV are 3 municipalities (Vanadzor, Gyumri, Pila). 30 municipal employees will be capacitated through the peer learning (study tours) to have key roles in renewing urban governance policies and running upgraded green infrastructure (eco-transportation and waste recycling facility). Relevant and interested CSOs, 2,000 residents, and4,000 school-children from 40 schools, as well as higher education institutions, vocational and educational training (VET) institutions in order to reach future teachers, managers and entrepreneurs, private business owners, larger employers and cultural institutions of target cities will directly benefit from environmental education and training. A Final Beneficiaries are 90,000 residents of Vanadzor, 120,000 residents of Gyumri, and 70,000 residents of Pila: they will benefit from better policies, improved public spaces due to local green deal initiatives, will have access to a cleaner environment due to eco-transportation, waste separation, and recycling, will be aware of adverse effects of carbon emissions on health and environment. 30 municipalities from Armenia and EU/EaP will benefit from participating in the networking conference on sustainable urban governance.

## Specific work

4.2.1 The Level of Effort for the expert is set out below:

| N | Tasks | Expert days (up to) | Expert daysfor 2021 (up to) |
| --- | --- | --- | --- |
|  | Provide input in drafting policy and legal documents on waste management and recycling issues in Vanadzor and Gyumri based on the priorities identified by taskforce members, assist in finalizing policy and legal document | 17 | 15 |
|  | Provide assistance in developing terms of reference related to the waste management equipment and facilities within the framework of the project. | 17 | 17 |
|  | Provide consultancy and technical assistance to Vanadzor and Gyumri municipalities in developing waste management plans. | 27 | 17 |
|  | Provide input in preparing public information, awareness raising and educational materials related to waste management and recycling. | 10 | 6 |
|  | Provide report and recommendations on the assignment | 4 | 3 |
|  | Total | 75 | 58 |

The schedule of tasks for the following years will be given in the form of an annex to the contract.

4.2.2 Key Qualifications

- University degree in Govenance, Social Sciences, or Environment, master’s degree is an advantage. Or, in the absence of a university degree, minimum of 1 additional year of professional experience on top of the 3 years.

- Knowledge of waste management context and policies.

- At least 3 years of proven practical experience in the waste management sector including during last 3 years.

- At least 3 years of experience in developing waste management strategic plans using participatory methods including duiring last 3 years. As well as practical work with governments, wtih the Ministry of Territorial Administration and Infrastructure, international organizations which implemented projects in the fields of waste management policy and planning, will be advantage.

- Experience in economic calculation of unit cost of solid waste collection, accumulation, transportation and disposal. This experience should include last 3 years.

- Expereince in writing policy papers and making policy recommendations in waste management.

- Familiarity with European practicies of waste management.

- Demonstrate clear and concise written skills in English. as well as high-quality skills in dialogue and presentation of information (knowledge of English).

- Any combination of education and experience which provides the tenderer with the desired skills, knowledge, and ability required to perform the job.

## Project management

### Responsible body

“Vanadzor Municipality Staff” Community Management Institution, represented by ABC.GoV Project.

### Management structure

Vanadzor Municipality will coordinate all aspects of the technical assistance through the Alliance for Better City Governance (ABC.GoV) Project.

# LOGISTICS AND TIMING

## Location

Vanadzor and Gyumri Cities, Armenia.

## Start date &period of implementation of tasks

The intended start date is 04 October 2021 and the period of implementation of the contract will be 32 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

Provisionally, the contract will be signed for 12 months and will be extended automatically beyond that period upon availability of funds by contracting authority.

Concrete start date of each task and detailed task descriptions will be provided in the contract related to each task.

The time-line of tasks for the following years will be provided in the contact.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# MONITORING AND EVALUATION

## Definition of indicators

Monitoring and evaluation of the activity will be provided in accordance with the Vanadzor Municipality's policies and procedures.

Recommendation 351 (2014): English version: https://wcd.coe.int/ViewDoc.jsp?id=2170873&Site=COE; Armenian version: http://www.coe.am/docs/clrae/report1.pdf